## 2025
Timeline for Review by Board of Curators
For Consideration at the:
ACTION | FEBRUARY 2025 (Meeting at UMKC) | APRIL 2025 (Meeting at S&T) | JUNE 2025 (TBD) | SEPTEMBER 2025 (Meeting at MU) | NOVEMBER 2025 (Meeting at UMSL)
Recommended deadline for full proposal submission.* | 2024-10-04 | 2025-01-10 | 2025-03-21 | 2025-06-06 | 2025-08-15 | -33 | 5 weeks prior to date below. Friday of that week.
Recommended deadline to begin system-wide campus reviews.** | 2024-11-01 | 2025-02-12 | 2025-04-23 | 2025-07-09 | 2025-09-17 | -28 | 4 weeks prior to date below
Recommended deadline to conclude system-wide review. | 2024-12-20 | 2025-03-12 | 2025-05-21 | 2025-08-06 | 2025-10-15 | -7 | 1 week prior to date below
Deadline to submit final version of proposal to Academic Affairs. | 2025-01-08 | 2025-03-19 | 2025-05-28 | 2025-08-13 | 2025-10-22 | -14 | 2 weeks prior to date below
Deadline to submit to Board Office. | 2025-01-22 | 2025-04-02 | 2025-06-11 | 2025-08-27 | 2025-11-05 | -15 | 15 days prior to BOC mtg
Dean/Proposal Lead Present at Board of Curators' Meeting | 2025-02-06 | 2025-04-17 | 2025-06-26 | 2025-09-11 | 2025-11-20 |  | FEBRUARY DATES ARE DIFFERENT DUE TO HOLIDAY BREAKS. USE #S BELOW
| NOTE: To calculate future dates, simply insert a date in the italics (bottom row) and all other dates above it will self-populate. | [5 empty] | -19 | -49 | -28
*Proposals may be submitted after this date. The amount of time required for the full proposal review stage is dependent upon several factors, including the quality of the first submission and the number of modifications needed as well as the number of proposals currently under review by the Office of Academic Affairs. | [6 empty] | CHANGE # TO REFLECT 1 WEEK AFTER FALL SEMESTER ENDS | CHANGE # TO REFLECT 1ST FRIDAY IN NOVEMBER | CHANGE # TO REFLECT 1ST FRIDAY IN OCTOBER
**Proposals are sent to the other three universities, which have 20 days to submit comments. These comments may require additional modifications to be made by the proposing campus.
Formulas:
FEBRUARY 2025 (Meeting at UMKC) = [FEBRUARY 2025 (Meeting at UMKC), row below]+J10
FEBRUARY 2025 (Meeting at UMKC) = [FEBRUARY 2025 (Meeting at UMKC), row below]+I10
APRIL 2025 (Meeting at S&T) = [APRIL 2025 (Meeting at S&T), row below]+G4
JUNE 2025 (TBD) = [JUNE 2025 (TBD), row below]+G4
SEPTEMBER 2025 (Meeting at MU) = [SEPTEMBER 2025 (Meeting at MU), row below]+G4
NOVEMBER 2025 (Meeting at UMSL) = [NOVEMBER 2025 (Meeting at UMSL), row below]+G4

## 2024
Timeline for Review by Board of Curators
For Consideration at the:
ACTION | FEBRUARY 2024 (Meeting at MU) | APRIL 2024 (Meeting at S&T) | JUNE 2024 (Springfield, MO) | SEPTEMBER 2024 (Meeting at UMKC) | NOVEMBER 2024 (Meeting at UMSL)
Recommended deadline for full proposal submission.* | 2023-10-06 | 2024-01-12 | 2024-03-22 | 2024-06-07 | 2024-08-15 | -33 | 5 weeks prior to date below. Friday of that week.
Recommended deadline to begin system-wide campus reviews.** | 2023-11-03 | 2024-02-14 | 2024-04-24 | 2024-07-10 | 2024-09-17 | -28 | 4 weeks prior to date below
Recommended deadline to conclude system-wide review. | 2023-12-22 | 2024-03-13 | 2024-05-22 | 2024-08-07 | 2024-10-15 | -7 | 1 week prior to date below
Deadline to submit final version of proposal to Academic Affairs. | 2024-01-10 | 2024-03-20 | 2024-05-29 | 2024-08-14 | 2024-10-22 | -14 | 2 weeks prior to date below
Deadline to submit to Board Office. | 2024-01-24 | 2024-04-03 | 2024-06-12 | 2024-08-28 | 2024-11-05 | -15 | 15 days prior to BOC mtg
Dean/Proposal Lead Present at Board of Curators' Meeting | 2024-02-08 | 2024-04-18 | 2024-06-27 | 2024-09-12 | 2024-11-20 |  | FEBRUARY DATES ARE DIFFERENT DUE TO HOLIDAY BREAKS. USE #S BELOW
| NOTE: To calculate future dates, simply insert a date in the italics (bottom row) and all other dates above it will self-populate. | [5 empty] | -19 | -49 | -28
*Proposals may be submitted after this date. The amount of time required for the full proposal review stage is dependent upon several factors, including the quality of the first submission and the number of modifications needed as well as the number of proposals currently under review by the Office of Academic Affairs. | [6 empty] | CHANGE # TO REFLECT 1 WEEK AFTER FALL SEMESTER ENDS | CHANGE # TO REFLECT 1ST FRIDAY IN NOVEMBER | CHANGE # TO REFLECT 1ST FRIDAY IN OCTOBER
**Proposals are sent to the other three universities, which have 20 days to submit comments. These comments may require additional modifications to be made by the proposing campus.
Formulas:
FEBRUARY 2024 (Meeting at MU) = [FEBRUARY 2024 (Meeting at MU), row below]+J10
FEBRUARY 2024 (Meeting at MU) = [FEBRUARY 2024 (Meeting at MU), row below]+I10
APRIL 2024 (Meeting at S&T) = [APRIL 2024 (Meeting at S&T), row below]+G4
JUNE 2024 (Springfield, MO) = [JUNE 2024 (Springfield, MO), row below]+G4
SEPTEMBER 2024 (Meeting at UMKC) = [SEPTEMBER 2024 (Meeting at UMKC), row below]+G4
NOVEMBER 2024 (Meeting at UMSL) = [NOVEMBER 2024 (Meeting at UMSL), row below]+G4